## Slide 1: Is a 50% Reduction of Government Documents Space Possible? - The Curation Weeding Dance
Presented by: Agnes Zientarska-Kayko
Dana Porter Library

## Slide 2: Agenda
Planning
Process
Conclusions / Lessons learned

## Slide 3: Planning
The story behind the project
University of Waterloo Library approach:
  6000 or more linear feet of government documents
  Needed to regain 3500 linear feet
  Couldn’t afford time or resources to do title by title review

## Slide 4: Planning
What does Strategic Retention mean?
Retain
Review (curate)
Withdraw

## Slide 5: Planning - Strategic Retention Flow Chart
Strategic Retention
Known or easily identified
Retain long term
Relocate to review
Unknown - what we will come upon as we develop Strategic Retention Plan
Retain to digitize
Strategic
Gems (flag for appraisal)
LTR -Porter
LTR- On Campus (Davis basement)
LTR - Off campus
Withdraw
LTR- Porter
LTR - On campus
LTR - Off site
Retain long term
Withdraw
LTR - Porter
LTR - on campus
LTR - off site
Once digitized - withdraw

## Slide 6: Planning - Strategic Retention Goals
Retain 50% of Government Documents collection
Commit to retain materials long term
Allow users easier access to our government documents by improving their discoverability
Retain, host, preserve and digitize strategic regional government documents

## Slide 7: Planning
Collection Development Policy for Government Documents
Identify strategic retention areas
  Transformational research themes
  Campus priority research areas
  Research Chairs focuses
  Who on campus needs government documents?
Identify high level corporate authors whose publications in those areas we likely want to keep

## Slide 8: Planning

## Slide 9: Planning
Criteria for retention, relocation or withdraw:
Relevance to curriculum, research and general collection
Historical value
Value of publication to community
What will not be kept by others

## Slide 10: Planning
Break collection down into more manageable sections
Identify specific search terms within strategic retention areas
Tag specified concepts and search terms by list
Identify quick wins
  Long runs
  Visual inspection for monographs
  Online availability

## Slide 11: Planning

## Slide 12: Planning

## Slide 13: Process – Staff directly involved
Information Services and Resources – Manager, GP Librarian, Liaison Librarians (8), Contract Staff (6 months), Co-op Students (2)
Collection Management – Manager, Project Coordinator, Collection Maintenance Analyst , Contract staff (3), Student Staff (6)
Cataloguing – Dept. Head, Cataloguer, Co-op Student
Special Collections - Archivist

## Slide 14: Process -Timeline
Winter - Spring 2016 – planning begins
Spring - Summer 2016 – consultations with librarians, tagging
Summer 2016 – pulling starts
Fall 2016 - Spring 2017 – pulling continues
July 3 2017 – packing of the floor starts
August 2018 – government docs are back in the library!

## Slide 15: Process – Quick wins
International government documents (mix and match of content)
Visual Inspection Monograph Project
  LC re-class and transfer books to the stacks
  Discard
Long runs
Electronic access

## Slide 16: Process – Working with lists
International (UK, UN, USA, EU)
Canada - Federal
Provinces
  Ontario
  Other Provinces
Region of Waterloo
Waterloo, Kitchener, Cambridge
Reference Collection

## Slide 17: Process – Working with lists

## Slide 18: Process
Items pulled using Withdraw Pull List
Discard temporary location assigned
Items not found on the shelf investigated
Global deletion process
  Removing fines
  Identifying records linked to orders
  Updating records

## Slide 19: Conclusions /Lessons Learned
List of GP’s included:
145,926 – total number of items
74,729 – total number of bib records
70,002 – items withdrawn

## Slide 20: Conclusions / Lessons learned
Communication with stakeholders
Collaboration across departments is a must
People will be upset
Be prepared to accommodate researchers requests

## Slide 21: Conclusions / Lessons learned
“Fun” Facts
Missing documents
Government docs from other locations found
Documents already deleted from the catalogue found on the shelves
Problems with the list and call numbers sorting
Problems with tagging

## Slide 22: Conclusions / Lessons learned
What worked?
Creating lists and sub lists for selectors to review (CA1, International, UK, UN, USA, EU, etc.)
Team work between three departments (ISR, Cataloguing, Circulation Maintenance)
GP Monograph Review and LC re-class
Search development work done by contract employee with cataloguing background

## Slide 23: Conclusions / Lessons learned
What didn’t work?
Critical corporate authors
Necessary to ‘touch’ more materials than we expected
Longest run lists as first pass – other retention criteria needed to be applied first
TUG efforts to collaborate on deselection of materials

## Slide 24: Government Documents Collection

## Slide 25
Agnes Zientarska-Kayko
azientar@uwaterloo.ca